## Sheet1
EPT Deliverable Status of As May 12
This report lists the status of EPT practices' deliverable submission for the November 2024 and May 2025 milestone submission. Deliverables are listed with one of six statuses, which are described below. The Learning Center encourages that practices and stakeholdesr use this report to track deliverables progress and to ensure all deliverables are submitted by the deadline. •Resubmit: Practices who have been asked for minor clarification on their deliverables. Resubmissions are due by May 19th. • Submitted: These deliverables have been submitted by practices to the Learning Center during the May 2025 submission and are being reviewed. • Accepted: This applies to the empanelment assessment, empanelment policy and procedure, and data governance & HEDIS assessment and policy and procedure that were submitted in Nov 2024, deliverables that are “accepted” are eligible for EPT payment. For the KPI assessment, practices are eligible for payment once they have met the measure benchmark as described in the EPT milestones document. • Didn't Submit: The Learning Center has not recieved this deliverable from the practice. • Rejected: Deliverables are listed as “rejected” if the practice submitted the deliverable, but it did not meet milestone criteria. • Attested Out: Practices who "attested out" of empanelment were not eligible to submit the empanelment assessment or the policy and procedure.
Practice Name | EPT ID | Sponsor Managed Care Plan | Key Performance Indicators Nov 2024 | Key Performance Indicators May 2025 | Empanelment & Access Assessment | Empanelment & Access Policy & Procedure | Data Goverance Assessment | Data Governance Policy & Procedure | Data Implementation Plan | Stratified HEDIS Like Measures | 2024 PhmCAT | 2025 PhmCAT
APLA Health | 335 | L.A. Care Health Plan | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Acacia Family Medical Group | 516 | Central California Alliance for Health | Not Started | Submitted | Submitted | Submitted | Submitted | Accepted | Submitted | Submitted | Accepted | Accepted
Adventist Health Delano | 669 | Kern Family Health Care | Not Started | Not Started | Accepted | Not Started | Submitted | Not Started | Not Started | Not Started | Accepted | Accepted
Ajitpal S Tiwana MD | 29 | Kern Family Health Care | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Not Started | Submitted | Accepted | Accepted
Alameda Health System | 657 | Alameda Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Alexander Valley Healthcare | 336 | Partnership Health Plan of California | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Aliya I Ali MD | 106 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
All for Kids | 449 | Health Plan of San Joaquin | Accepted | Submitted | Accepted | Accepted | Submitted | Accepted | Submitted | Not Started | Accepted | Accepted
Allied Health Solutions Medical Group | 189 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
American Indian Health & Services | 270 | CenCal Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
American Pediatrics | 33 | Inland Empire Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Ampla Health | 303 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Annapoorani Thenappan MD Inc | 328 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Annette Coronel Perey MD Inc | 243 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Aria Community Health Center | 140 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Aruna Pallapati, MD | 719 | Inland Empire Health Plan | Accepted | Submitted | Accepted | Resubmit | Accepted | Resubmit | Submitted | Submitted | Accepted | Accepted
Arvin Medical Clinic | 425 | Kern Family Health Care | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Asian Pacific Health Care Venture | 353 | L.A. Care Health Plan | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Aspen Family Medical Group of Modesto | 122 | Health Plan of San Joaquin | Accepted | Submitted | Accepted | Submitted | Submitted | Accepted | Not Started | Not Started | Accepted | Accepted
Atalla Medical Group | 3 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Avala Pediatrics | 177 | Health Net Community Solutions Inc. | Accepted | Not Started | Accepted | Accepted | Accepted | Accepted | Not Started | Not Started | Accepted | Not Started
Baechtel Creek Medical Clinic | 146 | Partnership Health Plan of California | Accepted | Not Started | Accepted | Accepted | Accepted | Accepted | Not Started | Not Started | Accepted | Accepted
Barton Health System | 66 | Health Plan of San Joaquin | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Bartz Altadonna Community Health Center | 130 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Bendito Medical Corporation | 670 | Inland Empire Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Bendito Pediatrics Inc | 547 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Binh Le MD | 567 | Health Net Community Solutions Inc. | In Progress | Submitted | Submitted | Submitted | Submitted | Submitted | Not Started | Not Started | Accepted | Accepted
CHOICE Health Network | 663 | CalOptima | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | In Progress | Submitted | Accepted | Accepted
Camino Health Center | 507 | CalOptima | Accepted | Submitted | Accepted | Submitted | Accepted | Submitted | Submitted | Submitted | Accepted | Accepted
Capitol Family Medical Associates | 543 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Cardin HealthCare Inc | 207 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Caspian Medical Clinic | 443 | Health Net Community Solutions Inc. | Accepted | Not Started | Accepted | Accepted | Accepted | Accepted | Not Started | Not Started | Accepted | Not Started
Cedars Family Medicine | 644 | CalOptima | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Celebrating Life Community Health Center | 573 | CalOptima | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Center4Health Medical Group | 56 | L.A. Care Health Plan | Accepted | In Progress | Accepted | Resubmit | Accepted | Accepted | In Progress | In Progress | Accepted | Accepted
Centinela Medical Group | 28 | L.A. Care Health Plan | In Progress | Not Started | Submitted | Submitted | Submitted | Submitted | Not Started | Not Started | Accepted | Accepted
Chapa-De Indian Health Program | 245 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Not Started | Submitted | Accepted | Accepted
Children's Hospital of Orange County (CHOC Childrens) | 647 | CalOptima | Accepted | Submitted | Accepted | Accepted | Submitted | In Progress | In Progress | In Progress | Accepted | Accepted
Children's Primary Care Medical Group | 621 | Inland Empire Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Chinatown Service Center (CSC Health) | 98 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
City Medical Group | 100 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Clinica Agua Viva | 690 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Clinica Medica Familiar | 720 | CalOptima | Accepted | Submitted | Accepted | Submitted | In Progress | Submitted | Not Started | In Progress | Accepted | In Progress
Clinica Msr. Oscar A. Romero | 555 | L.A. Care Health Plan | Not Started | Submitted | Accepted | Accepted | Accepted | Submitted | In Progress | Submitted | Accepted | Accepted
Clinica del Socorro Medical Group Inc | 1 | L.A. Care Health Plan | Accepted | In Progress | Accepted | Resubmit | Accepted | Accepted | Submitted | In Progress | Accepted | Accepted
Clovis Pediatric Group | 293 | CalViva Health | Not Started | Submitted | Submitted | Accepted | Submitted | Accepted | Not Started | Not Started | Accepted | Accepted
Coalinga Valley Health Clinics | 283 | Health Net Community Solutions Inc. | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Accepted | Not Started
Coastal Kids | 296 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Community Health Centers of America | 503 | Central California Alliance for Health | Not Started | Not Started | Submitted | Submitted | Submitted | Accepted | Not Started | Not Started | Accepted | Not Started
Community Pediatric Clinic Inc | 152 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | In Progress | Accepted | Accepted
Comprehensive Community Health Centers | 181 | L.A. Care Health Plan | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
County of Santa Barbara Public Health Department | 367 | CenCal Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
De Novo Health Care | 116 | Health Net Community Solutions Inc. | Accepted | Not Started | Accepted | Resubmit | Accepted | Accepted | Not Started | Not Started | Accepted | Not Started
Denise A. Albury MD | 75 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Not Started | In Progress | Accepted | Accepted
Docs for Kids | 44 | CalOptima | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Doctors on Duty Medical Group | 65 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Dung My Phan MD | 160 | Santa Clara Family Health Plan | Not Started | Submitted | Submitted | Accepted | Submitted | Accepted | Not Started | Not Started | Accepted | Accepted
Eastern Plumas Health Care | 173 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Submitted | Accepted | Submitted | Submitted | Accepted | Accepted
El Dorado Community Health Centers | 382 | Health Plan of San Joaquin | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Not Started | Submitted | Accepted | Accepted
El Proyecto del Barrio | 631 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Eloy Romero, M.D. Inc. | 444 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | In Progress | Submitted | Accepted | Accepted
Emanate Health Medical Group | 363 | Health Net Community Solutions Inc. | Accepted | Not Started | Accepted | Resubmit | Accepted | Accepted | Not Started | Not Started | Accepted | Not Started
Fairway Children's Medical Group | 433 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Families Together of Orange County | 464 | CalOptima | Accepted | Submitted | Submitted | Submitted | Submitted | Accepted | Accepted | Submitted | Accepted | Accepted
Family Health Matters | 566 | CalOptima | Accepted | Submitted | Accepted | Submitted | Accepted | Submitted | Submitted | Submitted | Accepted | Accepted
Family Health Services Clinics | 411 | Partnership Health Plan of California | Accepted | Not Started | Accepted | Resubmit | Accepted | Resubmit | Not Started | Not Started | Accepted | Not Started
Fariborz David Satey MD Inc - Dr. Satey's Pediatrics | 439 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Submitted | In Progress | Accepted | Accepted
Feras and Hisham | 468 | L.A. Care Health Plan | Accepted | In Progress | Accepted | Accepted | Accepted | Accepted | Submitted | In Progress | Accepted | Accepted
First Pediatrics Medical Group | 624 | CalViva Health | Not Started | In Progress | Submitted | In Progress | Submitted | In Progress | In Progress | In Progress | Accepted | Accepted
Florence Medical Center | 361 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Resubmit | Accepted | Accepted | Not Started | Submitted | Accepted | Accepted
Florence Western Medical Clinic and Medicina Familiar Medical Group | 282 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Not Started | Accepted | Accepted
Gage Medical Clinic | 26 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Not Started | In Progress | Accepted | Accepted
Galt Medical Center | 607 | Health Net Community Solutions Inc. | Not Started | Submitted | Accepted | Accepted | Accepted | Accepted | Not Started | Submitted | Accepted | Accepted
Gardens Medical Center | 120 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Garfield Health Center | 351 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Golden Oak Pediatrics | 715 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | In Progress | Not Started | Accepted | Accepted
Good Samaritan Health Center Wasco | 445 | Kern Family Health Care | Accepted | Not Started | Accepted | Resubmit | Accepted | Accepted | Not Started | Not Started | Accepted | Not Started
HEAL Medical Group | 403 | Molina Health Care of California Partner Plan Inc | Not Started | Submitted | Submitted | Submitted | Submitted | Accepted | Accepted | Submitted | Accepted | Accepted
Hamsa Ramkumar MD | 105 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Hanaa Hanna MD | 304 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Harjit Gogna MD | 486 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Not Started | In Progress | Accepted | Accepted
Harmony Health | 295 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Herald Christian Health Center | 434 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Hien Truong, MD, Inc | 24 | Santa Clara Family Health Plan | Not Started | Submitted | Submitted | Not Started | Submitted | Not Started | Not Started | Not Started | Accepted | Accepted
Hollister Pediatrics | 451 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Imperial Beach Community Clinic | 459 | Molina Health Care of California Partner Plan Inc | In Progress | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Indian Health Center of Santa Clara Valley | 497 | Santa Clara Family Health Plan | Accepted | Submitted | Accepted | Accepted | Submitted | Accepted | Submitted | Submitted | Accepted | Accepted
Indira Vemuri, MD | 591 | Santa Clara Family Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | In Progress | Accepted | Accepted
Isaias De Guzman Paja Jr MD | 129 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Issac Haddad MD | 174 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
JWCH Institute | 21 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Jackyln Chan MD | 211 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Jasleen Tiwana MD | 32 | Kern Family Health Care | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Not Started | Submitted | Accepted | Accepted
Javier Amu MD | 583 | CalViva Health | Accepted | Submitted | Submitted | Submitted | Submitted | Accepted | Accepted | Submitted | Accepted | Accepted
KCS | 252 | CalOptima | Accepted | Submitted | Accepted | Submitted | Submitted | Accepted | In Progress | Submitted | Accepted | Accepted
Karing Pediatrics | 605 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Kaweah Health | 110 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Submitted | Submitted | Submitted | Submitted | Submitted | Accepted | Accepted
Kedren Community Health Center | 34 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Kern Medical | 629 | Kern Family Health Care | Accepted | Submitted | Submitted | Not Started | Submitted | Not Started | Resubmit | Submitted | Accepted | Accepted
Kheir Clinic | 224 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Resubmit | Submitted | Accepted | Accepted
Kids and Teens Medical Group | 45 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Kimaw Medical Center | 604 | Partnership Health Plan of California | Accepted | Submitted | Submitted | Accepted | Not Started | Not Started | Not Started | Not Started | Accepted | Accepted
Las Americas Medical Clinic | 698 | L.A. Care Health Plan | Resubmit | Not Started | Accepted | Resubmit | Accepted | Resubmit | Not Started | Not Started | Accepted | Not Started
Lassen Indian Health Center | 258 | Partnership Health Plan of California | Not Started | Not Started | In Progress | Not Started | Accepted | Not Started | Not Started | Not Started | Accepted | Not Started
Lelanie M. Luna MD | 284 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Livingston Community Health | 297 | Health Plan of San Joaquin | Not Started | Submitted | Submitted | Accepted | Submitted | Accepted | Submitted | Submitted | Accepted | Accepted
Long Beach Family Clinic | 432 | Health Net Community Solutions Inc. | Not Started | Submitted | In Progress | In Progress | Submitted | Accepted | In Progress | Submitted | Accepted | Accepted
Madera Family Medical Group | 527 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | In Progress | Not Started | Accepted | Accepted
Majestic Medical Clinic | 386 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | In Progress | Accepted | Accepted
Mallu Reddy MD | 12 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | In Progress | Accepted | Accepted
Maria Teresa Pastor MD | 414 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Mariya Zakiuddin, MD | 204 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Mee Memorial Healthcare System | 151 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Submitted | Accepted | Accepted | Submitted | Accepted | Accepted
Merced Faculty Associates Medical Group | 329 | Central California Alliance for Health | Accepted | Submitted | Accepted | Not Started | Submitted | In Progress | Submitted | Submitted | Accepted | Accepted
Mission Medical Group | 519 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Submitted | Accepted | Not Started | Not Started | Accepted | Accepted
Mission Neighborhood Health Center | 592 | San Francisco Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Modern Concepts Medical Group | 359 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Mohan Kumaratne MD | 279 | CalOptima | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Mommy & Me Medical Group | 223 | Inland Empire Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Montage Medical Group | 321 | Central California Alliance for Health | Accepted | Submitted | Accepted | Not Started | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Mountain Valleys Health Centers | 334 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Submitted | Accepted | Not Started | Submitted | Accepted | Accepted
Next Door | 265 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | In Progress | Submitted | Accepted | Accepted
Nordhoff Medical Clinic | 169 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
North East Medical Services | 379 | San Francisco Health Plan | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Northeastern Rural Health Clinics | 278 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Not Started | Accepted | Not Started | Accepted | Submitted | Accepted | In Progress
Northern Valley Indian Health | 469 | Partnership Health Plan of California | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Accepted | Not Started
Omni Family Health | 574 | Kern Family Health Care | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | In Progress | Not Started | Accepted | Accepted
One Community Health | 620 | Anthem Blue Cross Partnership Plan | Not Started | Submitted | Submitted | Not Started | Submitted | Not Started | Not Started | Submitted | Accepted | Accepted
Open Door Community Health Centers | 509 | Partnership Health Plan of California | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Resubmit | Submitted | Accepted | Accepted
Opsam Health | 653 | Blue Shield of California Promise Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Pacific Central Coast Health Centers | 212 | CenCal Health | Accepted | Submitted | Accepted | Submitted | Submitted | Accepted | Not Started | Submitted | Accepted | Accepted
Pan and Hsu Pediatrics | 192 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Paul M. Baylon MD | 590 | Health Net Community Solutions Inc. | Accepted | Not Started | Accepted | Accepted | Accepted | In Progress | Not Started | Not Started | Accepted | Accepted
Peach Tree Health | 276 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Pediatric Care of Stockton | 148 | Health Plan of San Joaquin | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Not Started | Not Started | Accepted | Accepted
Pediatric Medical Associates | 299 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Petaluma Health Center | 633 | Partnership Health Plan of California | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Pinnacle Primary Care | 384 | Kern Family Health Care | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Pit River Health Services | 481 | Partnership Health Plan of California | Accepted | Submitted | Accepted | In Progress | Not Started | Not Started | Submitted | Submitted | Accepted | Accepted
Plazita Medical Clinic | 429 | Central California Alliance for Health | Not Started | Submitted | Submitted | Accepted | Submitted | Accepted | In Progress | Submitted | Accepted | Accepted
Polyclinic Medical Center | 318 | Kern Family Health Care | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Resubmit | Submitted | Accepted | Accepted
Precision Health Center | 392 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Premier Valley Medical Group | 442 | Kern Family Health Care | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Primary Care Solutions | 142 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Prime Medical | 82 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Resubmit | Submitted | Accepted | Accepted
Prime Wellness Community Health Center | 85 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Provident Primary Care | 406 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Rahul Grover MD | 649 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Submitted | In Progress | Accepted | Accepted
Ravenswood Family Health Network | 375 | Health Plan of San Mateo | Accepted | Submitted | Submitted | Accepted | Submitted | Accepted | Not Started | Submitted | Accepted | Accepted
Redwood Coast Medical Services | 548 | Partnership Health Plan of California | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | In Progress
Romie Lane Pediatric Group | 149 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Round Valley Indian Health Center | 416 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | In Progress | Submitted | Accepted | Accepted
Rural Health Network Inc. | 532 | Health Plan of San Joaquin | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | In Progress | Submitted | Accepted | Accepted
Sacramento Native American Health Center | 285 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Sacramento Valley Pediatric Medical Group | 654 | Health Net Community Solutions Inc. | Not Started | Submitted | Accepted | Resubmit | Accepted | Accepted | In Progress | Submitted | Accepted | Accepted
Saint Nazarene Medical Clinic | 417 | Health Net Community Solutions Inc. | Not Started | Submitted | Submitted | Accepted | Submitted | Accepted | Submitted | Submitted | Accepted | Accepted
Saint Youstina | 461 | CalOptima | Not Started | Submitted | Submitted | Submitted | Submitted | Submitted | Resubmit | Submitted | Accepted | Accepted
Salinas Pediatric Medical Group | 159 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Salud Para La Gente | 261 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
San Antonio Medical Center | 393 | CalOptima | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Resubmit | Submitted | Accepted | Accepted
San Diego American Health Center | 504 | Community Health Group Partnership Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
San Lucas Pediatric Clinic | 513 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Santa Cruz Community Health Centers | 627 | Central California Alliance for Health | Accepted | Submitted | Accepted | Accepted | Submitted | Submitted | Submitted | Submitted | Accepted | Accepted
Santa Lucia Medical Group | 596 | Central California Alliance for Health | Accepted | Submitted | Accepted | Submitted | Submitted | Submitted | In Progress | Submitted | Accepted | Accepted
Santo Nino Health Center | 652 | Health Net Community Solutions Inc. | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Accepted | Not Started
School Health Clinics of Santa Clara County | 317 | Santa Clara Family Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Sequoia Quality Health | 42 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Resubmit | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Serve the People Community Health Center | 109 | CalOptima | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Shasta Community Health Center | 301 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
SoHum Health | 188 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Resubmit | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Sonoma County Indian Health Project | 681 | Partnership Health Plan of California | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
St. Elizabeth Hospital Lassen Medical Clinic | 307 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
St. John's Community Health | 599 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Stallant Health and Wellness | 262 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Sunshine Pediatrics | 95 | Inland Empire Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
T.H.E. Health & Wellness Centers | 496 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Talat Saifee MD | 206 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
The Children's Clinic of Bakersfield | 426 | Kern Family Health Care | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
The Children's Doctor | 291 | Inland Empire Health Plan | Not Started | Submitted | Submitted | Submitted | Submitted | Resubmit | Submitted | Submitted | Accepted | In Progress
Todos Para La Salud | 273 | L.A. Care Health Plan | Not Started | In Progress | Accepted | Submitted | Accepted | Accepted | Not Started | In Progress | Accepted | Accepted
Toni D. Johnson Chavis MD | 117 | Health Net Community Solutions Inc. | Accepted | Not Started | Accepted | Resubmit | Accepted | Accepted | Not Started | Not Started | Accepted | Not Started
Tuolumne Me-Wuk Indian Health Center | 683 | Anthem Blue Cross Partnership Plan | Accepted | Submitted | Submitted | Accepted | Not Started | Not Started | Not Started | Submitted | Accepted | Accepted
United Indian Health Services, Inc. | 69 | Partnership Health Plan of California | Not Started | Not Started | Accepted | Not Started | Accepted | Not Started | Not Started | Not Started | Accepted | Not Started
Universal Healthcare Services | 25 | Kern Family Health Care | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
University Muslim Medical Association, Inc. | 626 | L.A. Care Health Plan | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Valley Community Healthcare | 302 | L.A. Care Health Plan | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Valley Pediatrics | 60 | Health Net Community Solutions Inc. | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Via Care Community Health Center | 643 | L.A. Care Health Plan | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Vishwa Kapoor, MD | 71 | Community Health Plan of Imperial Valley | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Watts Healthcare Corporation | 405 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Resubmit | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
West County Health Centers | 164 | Partnership Health Plan of California | Accepted | Submitted | Not Started | Not Started | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Western Sierra Medical Clinic | 352 | Partnership Health Plan of California | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Not Started | Submitted | Accepted | Accepted
White Memorial Community Health Center | 170 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Accepted | Submitted | Accepted | Accepted
Wilmington Community Clinic | 523 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | In Progress | Not Started | Accepted | Accepted
Wynn Medical Center | 472 | L.A. Care Health Plan | Accepted | Submitted | Accepted | Submitted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted
Yvonne D'sylva, MD | 544 | Inland Empire Health Plan | Accepted | Submitted | Accepted | Accepted | Accepted | Accepted | Submitted | Submitted | Accepted | Accepted